## 17-239
Task Name | Estimate time (hour) | Take by | Actual Time | Status | Date Doing | Note
Design Database | 2 | Phan Phu Hung |  | Done
Show list Uesr | 0.75 | Phan Phu Hung |  | Done
Insert user | 0.5 | Phan Phu Hung |  | Done
Edit User | 0.5 | Phan Phu Hung |  | Done
Remove User | 1 | Phan Phu Hung |  | Done
Display all STUDENT | 0.5 | Phan Phu Hung |  | Done
Display all TEACHER | 0.5 | Phan Phu Hung |  | Done
Add student to Group | 1 | Phan Phu Hung |  | Done
Search User by name | 0.5 | Phan Phu Hung |  | Done
Insert group | 0.5 | Phan Phu Hung |  | Done
Search Group by ID | 0.5 | Phan Phu Hung |  | Done
Show list Student Of Group | 1 | Phan Phu Hung |  | Done
Search Student of Group by name | 1 | Phan Phu Hung |  | Done
Show Group for Teacher and list Student | 1 | Phan Phu Hung |  | Done
Show Schedule for teacher | 2 | Phan Phu Hung |  | Done
Check Attendance for Student | 1 | Phan Phu Hung |  | Done
Show the schedule for the previous week and the following week | 1 | Phan Phu Hung |  | Done
Show Group for Student and list Student, and list Course | 2 | Phan Phu Hung |  | Done
Show the schedule for the previous week and the following week, and Status Attendance | 0.5 | Phan Phu Hung |  | Done
Login with role | 3 | Nguyen Doan Quang |  | Done
Change Password of Student , Teacher | 2 | Nguyen Doan Quang |  | Done
Update Phone , Mail of student , teacher | 2 | Nguyen Doan Quang |  | Done
do use case diagram | 3 | Nguyễn Đoàn quang |  | Done
do ERD | 3 | Nguyễn Đoàn Quang |  | Done
insert Course | 0.5 | Nguyễn Anh Hiếu |  | Done
Edit Course | 0.5 | Nguyễn Anh Hiếu |  | Done
Remove Course | 0.5 | Nguyễn Anh Hiếu |  | Done
Search Course | 0.75 | Nguyễn Anh Hiếu |  | Done
insert Schedule | 3 | Nguyễn Anh Hiếu |  | Done
Edit Schedule | 1 | Nguyễn Anh Hiếu |  | Done
Delete Schedule | 3 | Nguyễn Anh Hiếu |  | Done
Show Schedule | 0.5 | Nguyễn Anh Hiếu |  | Done
Search Schedule | 1 | Nguyễn Anh Hiếu |  | Done
Search Teacher | 0.5 | Nguyễn Anh Hiếu |  | Done
Add Teacher | 1 | Nguyễn Anh Hiếu |  | Done